## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-7ffHEfg3UqySrAef7o8nGQAOvGO | Create Categories in backend | Completed | Completed | Medium | Nunez, Jorge Abraham | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | Sprint 6;Sprint 4
-bkrC4aL5Eejo_89RIC1AmQAN40M | Reccuring bills: frontend | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/02/2026 | Magno, Melanie |  |  | wont
1yt-qAOMK06sAcMrF05SBWQAJGgO | As a homeless individual, I want to be able to login on the app so I can keep my information saved between uses. | Completed | Completed | Medium | Liles, Aurora Elisabeth | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth
3bB4oe11802dPocPkQHVaGQAJTdP | As a user, I want to be able to view my net earnings calculated automatically by the app, so that I have to do as little math as possible. | Completed | Completed | Medium | Liles, Aurora Elisabeth | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 6
5jn-LvT0ok-xL4C0HCfOMmQAF3Uk | As a DINK family, we want to have financial tips so that we can see how to stick to a budget and save money better. | scrapped by Shaik | Completed | Medium |  | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 8
5qoYVN-KU0G-G4a9LcBK9WQAL4Dt | As a user, I want to be able to enter my spent and earned money, so that I can keep track of how much money I have in a certain time period. | Completed | Completed | Medium | Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 8
5tX_XMBV_Uqgf6arbdDf82QAMNzU | Implement home page | In Progress | Completed | Medium | Liles, Aurora Elisabeth;Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/13/2026 | Liles, Aurora Elisabeth
8i425qOyoEyMCky-ap2dFWQAP9_T | Budgeting logic in backend | Completed | Completed | Medium | Harold, Kaylee Willa;Nunez, Jorge Abraham | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 7
Aja_hXGaPEaY98ck9ghx9WQAOh-F | Budget page (Frontend-edit page)) | Completed | Completed | Medium | Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 8
AvM163KBrUWdASi2uadIQmQANyzw | As a user, I want to be able to enter my spent and earned money, so that I can keep track of how much money I have in a certain time period. | Completed | Completed | Medium | Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 9;Sprint 8
BGcuayRxNk6b2cbrCB5K9mQANYm7 | Reminders: Backend | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/02/2026 | Magno, Melanie |  |  | wont
BZJXVx1cA0KCWTzMt2ZIMGQAGqZg | customize homepage | Completed | Completed | Medium | Yang, Wei | Liles, Aurora Elisabeth | 03/13/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | All Sprints Somehow
GlLbfKuG3UWGO1ZX9NX_RGQAJyy- | As a DINK family, we want to have financial tips so that we can see how to stick to a budget and save money better. | scrapped by Shaik | Completed | Medium | Yang, Wei | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Yang, Wei |  |  | should
H8ffiaAYlkiepHo4kL3Vb2QACiru | As a user, I want to be able to set a goal of expenditures per month, so that I can manage how much I am spending. | scrapped by Shaik | Completed | Medium | Harold, Kaylee Willa | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | wont;should
Hnj9zuFnq0mFZkK3OSLsG2QAFnJm | As a user, I want to be able to enter my spendings, so that I can keep track of how much money I have in a certain time period. | Completed | Completed | Medium | Magno, Melanie | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 9
KqYmdnYkg0qF2_eoR34IXmQAHcY7 | Reccuring bills: backend | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/02/2026 | Magno, Melanie |  |  | wont
MvAwkwEE8Emf3sIsDBG8-2QAKE2E | User Authentication | Completed | Completed | Medium | Nunez, Jorge Abraham | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 7
PHecI4ounUCfpke1pfCuc2QAP0x0 | Category Verification | Completed | Completed | Medium | Nunez, Jorge Abraham | Harold, Kaylee Willa | 03/10/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 7;Sprint 8
QQK6HnnD90uJaLV4UshWVmQAHutr | Define Custom Categories | scrapped by Shaik | Completed | Medium | Nunez, Jorge Abraham | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | Sprint 7;Sprint 8 | It’s kind of working? not having user authentication caused it to throw a 401 error, so i tweaked it in my main branch and now it throws a 500 error. YAY i fixed it, it gives 200 codes now.
QbDfp3QQo06ji3e3NjWmvmQAGYqp | As a varied spender, I want to define custom categories and subcategories so that the budget matches my personal spending habits | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | wont
QvBYlRbFn06pryk1D7P9gGQACQ1r | Reminders: Frontend | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/02/2026 | Magno, Melanie |  |  | wont
RPIhMfRYHEK8iYj89Nb8LmQAF1Jp | Working on template for pie chart on Visual page | scrapped by Shaik | Completed | Medium | Yang, Wei | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Yang, Wei |  |  | must;should
ShOsfZBb7E6JHYrjNze5mWQAK0Od | Logout | In Progress | Completed | Medium | Liles, Aurora Elisabeth | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/12/2026 | Liles, Aurora Elisabeth
Tht42EBP3U6inIEvW1wsE2QAF52C | As a user, I want to be able to enter my earnings, so that I can keep track of how much money I have in a certain time period | Completed | Completed | Medium | Magno, Melanie | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 8
Xyp6YRF9EU6qfm3CEX1XqWQAAtCv | Unit Testing automation | Completed | Completed | Medium | Harold, Kaylee Willa;Nunez, Jorge Abraham | Nunez, Jorge Abraham | 03/10/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 9
YlE-ngD2CUimWPqRfz8cDGQAJVtW | Login/logout functionality | In Progress | Completed | Medium | Liles, Aurora Elisabeth;Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/13/2026 | Liles, Aurora Elisabeth
_U6OZ97QV0O6oJLRqWa9DGQAB0Xs | I am a retired boomer from corporate america, i am looking to see if the interest from my investment and social security will cover my monthly expenses * | Completed | Completed | Medium | Liles, Aurora Elisabeth | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 6
bDdcN60Z9UaCCsE_F4pGMGQABHwb | Nav Bar creation | Completed | Completed | Medium | Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | Sprint 3
e34Z47SkoEelyJHe6J5a2WQAKu_T | Scaffold JS code if there is time. | Completed | Completed | Medium | Harold, Kaylee Willa | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa
gVqXoRMtZUeYJgkX26lqx2QAN63d | As an individual who owns my own home (IN THIS ECONOMY??), so I want to be able to logout so no homeless person can log into my account. | Completed | Completed | Medium | Liles, Aurora Elisabeth | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 4
hxqUE9jN40qtLjU0NvY7-mQAFDLK | CSS and styling | Completed | Completed | Medium | Yang, Wei | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 9;All Sprints Somehow
kr7ELvEpsk2Gg7aCTb5QFmQALIwM | psycache buildup? | Completed | Completed | Medium | Harold, Kaylee Willa | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | Sprint 4;Sprint 5
mJwtrripCkqe_TwH1KzxMmQABr9F | As an incompetent individual, I want to be able to visualize my whole income to see where my bills are going towards (like a piechart or something that shows how much of my income has been utilized). | scrapped by Shaik | Not started | Medium | Yang, Wei | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/30/2026 |  |  |  | must
nNRkhAyvHUaFUFkTugydwGQAHizf | Fleshing out the editing page | Completed | Completed | Medium | Liles, Aurora Elisabeth;Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 9;Sprint 8
nTy6Krgco0eKK2VZz_bfP2QACRvu | As a user, I want to have a good colour scheme in any app i use, so that I can read anything even though I am colorblind. | Completed | Completed | Medium | Yang, Wei | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie |  |  | Sprint 7
po6XOWpgGUefh5gcGXQIdGQAPHDa | worked on research for design patterns we used | Completed | Completed | Low | Magno, Melanie | Magno, Melanie | 03/27/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 7;should
qjKcUjL2eE-f6era_9Bpr2QAHplE | Frontend Transaction logic | Completed | Completed | Medium | Liles, Aurora Elisabeth;Magno, Melanie | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 7;Sprint 8
sVjLO-E3lEW_bP8ReBMBY2QAFUu9 | As a DINK, my time is already very slim, so I want my transactions to be categorized so I spend less time manually organizing my spending. | Completed | Completed | Medium | Nunez, Jorge Abraham | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 7
tVaTVnr_mU-AmkObEWgCTGQAOjlK | As a user, I want to be able to view my net earnings calculated automatically by the app, so that I have to do as little math as possible. * | Completed | Completed | Medium | Liles, Aurora Elisabeth | Magno, Melanie | 04/02/2026 |  |  | false | false | 04/10/2026 | Liles, Aurora Elisabeth |  |  | Sprint 7
tup-SvxzJE-TVEaDpJ7LC2QAH8lr | As a graduating student that wants to budget for the future in order to save to purchase a house, I want to be able to log my biweekly paychecks as well as my monthly planning in order to estimate how much money I need to save per month. | scrapped by Shaik | Completed | Medium |  | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 04/30/2026 | Magno, Melanie
wbRCUVtEMUWW-NJG5VMKDWQAG4UR | As a homeless individual, I want to be able to login on the app so I can keep my information saved between uses. | Completed | Completed | Medium | Liles, Aurora Elisabeth | Harold, Kaylee Willa | 03/05/2026 |  |  | false | false | 03/05/2026 | Harold, Kaylee Willa |  |  | Sprint 4

## Plan name
Plan name | Budget Tracker
Plan ID | fozCtmE3VEa9BVrrxq8ZDmQAA30C
Date of export | 04/30/2026